## Release Backlog
SCRUM PROJECT: Facial Analyzer for Rhinoplasty Operation
BACKLOG
PRIORITY | SPRINT | USER STORIES | TASK TITLE | TASK DESCRIPTION | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
1 | 1 | As a developer, I want to be able to use the code from last year. | Run Last Year's Model | Download, install, and successfully run the code from last year's project. | 4 | In Progress |  | Not Started | 1
1 | 1 | As a developer, I want to understand which algorithm(s) would work best. | Research machine learning | Research and choose the best machine learning options for use. | 16 | Not Started |  | Completed | 4
1 | 1 | As a developer, I wanted to understand all of the current complications with the system. | Inspect and Review Current System | Review and inspect all of the complications of the system from the last updated version. | 16 | Not Started |  |  | 8
1 | 1 | As a developer, I want a defined class structure for the algorithm(s). | Design Class Structure | Design a class structure, including methods, variables, and constructors for the machine learning algorithm of choice. | 16 | Not Started |  |  | 16
2 | 2 | As a user, I want to be able to easily capture my face. | Easy Face Capture | Write code that allows you to use your laptop camera for the face photo. | 4 | Not Started |  |  | 40
1 | 2 | As a user, I want to be given several suggestions to pick the best one | Set and Variable different selections | Implement multiple built in methods for outputs with the different AIs | 16 | Not Started
1 | 2 | As a developer, I want to be able to freely change the number of changepoints on the face for the AI to manipulate | Set and Variable changepoints | Implement multiple built in methods for changepoints that can be interchanged | 16 | Not Started
2 | 2 | As a developer, I want to cultivate a database applicable to the machine learning algorithms implemented | Create and Solidify Database | Cultivate a database that has required images with appropriate dimensions for machine learning algorithms to classify and identify | 24 | Not Started
2 | 2 | As as user, I want the GUI to look neat and clean. | Simple but Effective GUI | Write code for a nice and cleaning looking GUI, making sure that it is not too complicated. | 8 | Not Started
1 | 2 | As a developer, I want to increase the marking of the landmarks on the face for better resolution. | Increasing the Landmarks on the Face | Write code to increase the marking of landmarks on the face. | 16 | Not Started
2 | 2 | As a developer, I want multiple machine learning algorithms to run simutaneously | Implement Multiple machine learning AIs | Implement multiple machine learning AIs and have them run together | 24 | Not Started
3 | 3 | As a user, I want proper documentation for running the code | Install and Run documentation | Create a github wiki that thoroughly explains how to install and run the code to allow outside users to successfully use the code. | 2 | Not Started
1 | 3 | As a developer I want to ensure that the design documents are accurate | Documentation | Fill out the required documents nearly and accurately. | 16 | In Progress
1 | 3 | As a user, I want to be able to input certain criteria (Bigger nose, smaller cheeks, etc.) | Set and Variable parameters | Implement weighted parameters based on the consumers needs that will change the output from the AI | 16 | Not Started
1 | 3 | As a user, I want to be able to refesh the set of suggestions if I am not satisfied. | Implement Machine learning re-execution Method | Impliment methods that allow for machine learning algorithm to execute for more suggestions based on different feedback | 24 | Not Started
2 | 3 | As a user, I want to be able to see other peoples faces compared to mine | Comparing Cluster Faces | Show user faces like theirs in order to compare and have for reference in machine learning algorithms | 16 | Not Started
3 | 3 | As a user, I want to be able to use the web application easily and efficiently | Web Application | Take a look at the web application and find better alternatives/ create one that the user can use effortlessly | 24 | Not Started
3 | 3 | As a developer, I want to be able to maintain the facial database through a global resource | Facial Database Upkeep | Make sure the database is constantly being updated to have new and more accurate faces | 16 | Not Started